## Lead
Complaint Redressal System
Group Number - 8
Team Lead & Backend Lead - Tariq Mohammed Sarfaraz
Frontend Lead - Umme Hani R.

## Status Meeting
Status Meeting Group - 8
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-03-22 | 9:30 | a | 11:00 | a | 5:00 | a
2022-03-23 | 9:30 | a | 11:00 | a | 5:00 | a
2022-03-24 | 9:30 | a | 11:00 | a | 5:00 | a
2022-03-25 | 9:30 | a | 11:00 | a | 5:00 | a
2022-03-27 | 9:30 | a | 11:00 | a | 5:00 | a
2022-03-28 | 9:30 | a | 11:00 | a | 5:00 | a

## Status Track
Project Status Check Report Team - 8
Sl no. | Employee ID | Name | Domain | Module | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
1 | 2486701 | Shinde Nikita Navanath | Front-end | Customer and Complaint | Created Component | Html and Css for Designing Webpage | Created Service and Model | Form Validation and Resolving Errors | Created UML | Documentation
2 | 2486997 | Shreya K S | Front-end | Manager | Created Component | Html and Css for Designing Webpage | Created Service and Model | Form Validation and Resolving Errors | Created UML | Documentation
3 | 2487717 | Sparsha Gowda G | Back-end | Customer | Created Model, Repository, Service and Controller | Created REST API's | Tested the functionality for API's | Resolved Errors | Created UML | Documentation
4 | 2482282 | Tanmay Ajeet Kumar | Back-end | Manager | Created Model, Repository, Service and Controller | Created REST API's | Tested the functionality for API's | Resolved Errors | Created UML | Documentation
5 | 2486600 | Tariq Mohammed Sarfaraz | Back-end | Engineer and Engineer Duty | Created Model, Repository, Service and Controller | Created REST API's | Tested the functionality for API's | Resolved Errors | Integrated Backend API's and Frontend Services | Documentation
6 | 2487435 | Umme Hani R | Front-end | Engineer, Home and About us | Created Component | Html and Css for Designing Webpage | Created Service and Model | Form Validation and Resolving Errors | Created UML | Documentation
7 | 2487155 | Vemula Poornima | Front-end | Admin | Created Component | Html and Css for Designing Webpage | Created Service and Model | Form Validation and Resolving Errors | Created UML | Documentation
8 | 2484912 | Vishwanath Mangond | Back-end | Feedback | Created Model, Repository, Service and Controller | Created REST API's | Tested the functionality for API's | Resolved Errors | Created UML | Documentation
9 | 2484070 | Yakkanti Chinnapareddy | Back-end | Complaint | Created Model, Repository, Service and Controller | Created REST API's | Tested the functionality for API's | Resolved Errors | Created UML | Documentation
10 | 2483780 | Yerasi Gopinatha Reddy | Front-end | Feedback | Created Component | Html and Css for Designing Webpage | Created Service and Model | Form Validation and Resolving Errors | Created UML | Documentation